## PCI DSS Gap Assessment
Skybridge Airlines – PCI DSS Gap Assessment
PCI DSS Requirement | Control Objective | Current State | Gap Identified | Risk Impact | Priority | Remediation Recommendation | Owner | Target Date
Req. 1 | Install and maintain network security controls to protect the cardholder data environment. | Network and application connectivity for the booking platform and mobile payment flows are assumed to exist, but PCI-focused segmentation documentation is not formally maintained. | Network segmentation and boundary documentation for payment-connected systems is incomplete. | Weak segmentation clarity may cause PCI scope confusion and increase exposure from connected systems. | High | Document payment environment boundaries, review segmentation design, and maintain PCI-focused network scope records. | IT Operations Manager | 2026-07-15
Req. 3 | Protect stored account data. | The environment is assumed to rely on a third-party processor to minimize direct cardholder data storage, but internal validation of storage practices is limited. | There is no formal validation showing that internal systems, logs, or support workflows do not store prohibited cardholder data. | Unnecessary storage of account data could create direct PCI non-compliance and higher exposure in case of compromise. | High | Validate storage practices across systems, logs, and support processes; document results and remediate any storage of prohibited data. | E-Commerce Platform Owner | 2026-06-30
Req. 4 | Protect cardholder data with strong cryptography during transmission over open, public networks. | Payment data is assumed to be transmitted securely to a third-party processor, but documented review of transmission security and integration points is incomplete. | Secure transmission controls and evidence for payment data flows are not formally documented. | Weak transmission governance could expose payment data in transit and weaken audit readiness. | High | Review payment transmission paths, confirm encryption practices, and retain evidence of secure transmission controls. | IT Operations Manager | 2026-06-25
Req. 6 | Develop and maintain secure systems and software. | The booking platform and mobile app follow change processes, but PCI-specific secure development and patch governance evidence is not consistently centralized. | Secure development and patching evidence for payment-related applications is incomplete or fragmented. | Security weaknesses in payment-connected applications could increase the risk of compromise and failed assessment readiness. | High | Centralize evidence of patching, secure change review, and application security practices for in-scope payment systems. | E-Commerce Platform Owner | 2026-07-20
Req. 7 | Restrict access to system components and cardholder data by business need to know | Role-based access exists for some systems, but access design and review expectations for payment-related systems are not fully formalized. | Least-privilege access for payment-connected systems is not consistently evidenced through formal review and role validation. | Excessive or outdated access may increase the risk of unauthorized exposure and weaken PCI control assurance. | High | Define access baselines for payment-related systems and implement documented periodic access reviews. | IAM Manager | 2026-06-20
Req. 8 | Identify users and authenticate access to system components. | Individual user access is assumed for most systems, but privileged access governance and recertification are not consistently documented for payment-related administration. | Privileged and administrative access to payment-connected systems is not fully governed through documented recertification and review. | Weak admin accountability may increase the risk of unauthorized changes or untraceable elevated access. | High | Formalize privileged access approval, MFA verification, and periodic recertification for payment-related administrative access. | IAM Manager | 2026-06-18
Req. 10 | Log and monitor all access to system components and cardholder data. | Logging is assumed for core systems, but PCI-focused logging scope, retention, and review evidence are not centrally tracked. | Logging and monitoring evidence for payment-related systems is incomplete and may not demonstrate consistent review. | Failure to retain and review relevant logs could weaken detection, investigation, and PCI assessment readiness. | High | Define PCI-relevant log sources, review cadence, retention expectations, and evidence ownership. | Security Operations Lead | 2026-07-10
Req. 11 | Test security of systems and network regularly | Security testing is assumed to occur at a general level, but PCI-targeted testing evidence for payment-connected systems is not clearly mapped. | There is no consolidated evidence showing regular security testing aligned to PCI expectations for in-scope systems. | Weak test evidence may leave exploitable weaknesses unidentified and create assessment gaps. | Medium | Map testing activities to in-scope systems, retain evidence, and define testing ownership and frequency. | Security Operations Lead | 2026-07-25
Req. 12 | Support information security with organisation policies and programs | Security and compliance policies are assumed to exist, but PCI-specific ownership, responsibility, and governance documentation is not fully structured. | PCI governance roles, evidence responsibilities, and review cadence are not clearly documented. | Weak governance can cause inconsistent control execution, poor evidence readiness, and slower remediation. | High | Define PCI governance responsibilities, control owners, and evidence management expectation | Head of Compliance | 2026-06-28
Req. 12 | Manage service providers with which account data is shared, or that could affect the security of account data. | Third-party payment processing is used, but service provider responsibility tracking and evidence collection are not fully formalized. | Service provider oversight for PCI-relevant vendors is not consistently documented. | Weak third-party oversight may leave critical security responsibilities unclear and weaken PCI accountability. | High | Formalize service provider PCI responsibility tracking, evidence collection, and periodic review. | Vendor Management Lead | 2026-07-05