## SkyBridge Airline – Privacy Com
Skybridge Airline – Privacy Compliance Assessment
Requirement ID | Regulation | Privacy Requirement | Current State | Gap Identified | Risk Impact | Priority | Recommended Action | Owner | Target Date | Status
P-001 | GDPR | Lawful basis for processing personal data | Customer data is collected through booking and payment flows, but lawful basis documentation is not consistently mapped | No formal record linking data processing activities to lawful basis | Regulatory exposure and weak privacy governance | High | Document lawful basis for each major processing activity and align privacy notices | Data Protection Officer | 2026-06-30 | Open
P-002 | GDPR | Data subject rights handling | Customer support can respond to some requests, but no formal workflow exists for access, deletion, or correction requests | Inconsistent process for handling data subject rights requests | Delayed response, non-compliance, customer trust issues | High | Create and document a formal data subject rights intake and response process | Customer Privacy Manage | 2026-07-15 | In Progress
P-003 | CCPA | Notice at collectio | General privacy notice exists, but collection-specific notice is limited across digital entry points | Consumers may not receive clear notice at or before data collection | Regulatory exposure and transparency weakness | High | Add collection notices to booking, app, and payment touchpoints | E-Commerce Platform Owner | 2026-06-25 | Open
P-004 | CCPA | Consumer right to opt out of data sharing | Data sharing with analytics and service providers is disclosed broadly, but opt-out workflow is not clearly operationalized | No clearly defined opt-out mechanism for applicable sharing activities | Consumer complaints and compliance risk | Medium | Define opt-out process and validate supporting technical controls | Privacy Compliance Lead | 2026-07-20 | Open
P-005 | GDPR / CCPA | Data retention and minimization | Customer and operational records are retained for extended periods without a fully documented retention schedule | Data retention periods and minimization standards are not consistently enforced | Increased privacy exposure and over-retention risk | High | Establish data retention schedule and align deletion standards across systems | Records Management Lead | 2026-08-01 | Open